## Sheet1
Day | Time spent (hh:mm) | Description
2017-11-28 | 0:10 | Set up project
2017-11-28 | 0:30 | Research original game
2017-11-28 | 1:10 | Trying to understand structure + get basic character with movement
2017-11-29 | 1:00 | Restructuring character + basic sword implementation + camera movement
2017-12-01 | 0:45 | Spawn enemies through manager + killable enemies
2017-12-01 | 0:45 | Basic inventory + enemy behaviour
2017-12-01 | 1:15 | HUD + attack power recharge for player
2017-12-01 | 0:50 | Character switching + inactive character follow player
2017-12-01 | 1:20 | UI panel system + character panel
2017-12-01 | 1:45 | Inventory panel + player sprinting
2017-12-02 | 1:45 | Consumable item + Health potion + Character panel show equiped stat boost
2017-12-02 | 0:55 | Inventory update when (un)equiping + Spear + Basic combat text